## C&S Build Estimates
MyBizz Consulting & Services — Build Cost Estimate
Estimates in ZAR. Actual costs recorded where available. All estimates based on Stage 1.2 actuals and scope analysis.
0
Stage | Pre-dev | UI Scope | UI Design | Code Draft | Code Polish | Local Testing | Uplink Testing | Checks | 0 | Days
PHASE 1 — Authentication & Administration
1.1 Project Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
1.2 Authentication System | 0 | 45.73 | 98.77 | 45.05 | 104.21 | 28.05 | 101.32 | 59.16 | 482.29 | 2
1.3 Dashboard & Navigation | 170 | 0 | 0 | 80 | 120 | 35 | 120 | 40 | 565 | 3
1.4 Settings & Configuration | 0 | 0 | 0 | 80 | 100 | 25 | 90 | 30 | 325 | 2
1.5 The Vault | 0 | 0 | 0 | 90 | 80 | 35 | 90 | 30 | 325 | 2
1.6 AdminLayout — Full Navigation | 0 | 0 | 0 | 50 | 60 | 20 | 50 | 25 | 205 | 1
PHASE 2 — Website & Content
2.1 Public Website — Standard Pages | 0 | 0 | 0 | 60 | 80 | 20 | 70 | 30 | 260 | 2
2.2 Home Page Templates | 0 | 0 | 0 | 80 | 110 | 25 | 80 | 30 | 325 | 2.5
2.3 Landing Pages System | 0 | 0 | 0 | 75 | 95 | 25 | 70 | 30 | 295 | 2
2.4 Blog System | 0 | 0 | 0 | 70 | 90 | 25 | 80 | 30 | 295 | 2
PHASE 3 — Payments & Invoicing
3.1 Payment Gateway (Stripe / Paystack) | 0 | 0 | 0 | 110 | 140 | 45 | 160 | 40 | 495 | 3.5
3.2 Invoicing System | 0 | 0 | 0 | 80 | 100 | 30 | 100 | 30 | 340 | 2
PHASE 4 — Bookings & Appointments
4.1 Calendar System | 0 | 0 | 0 | 100 | 120 | 35 | 120 | 35 | 410 | 3
4.2 Availability Management | 0 | 0 | 0 | 80 | 100 | 30 | 100 | 30 | 340 | 2
4.3 Booking Creation Flow | 0 | 0 | 0 | 90 | 120 | 35 | 120 | 35 | 400 | 2.5
4.4 Service Catalogue Management | 0 | 0 | 0 | 70 | 90 | 25 | 90 | 30 | 305 | 2
PHASE 5 — CRM & Marketing
5.1 Contact Management | 0 | 0 | 0 | 80 | 100 | 30 | 110 | 30 | 350 | 2
5.2 Email Marketing (Zoho Campaigns) | 0 | 0 | 0 | 110 | 140 | 35 | 150 | 35 | 470 | 3
5.3 Segmentation | 0 | 0 | 0 | 70 | 90 | 25 | 90 | 30 | 305 | 1.5
5.4 Task Automation | 0 | 0 | 0 | 80 | 100 | 30 | 100 | 30 | 340 | 1.5
PHASE 6 — Security & Compliance
6.1–6.8 Security, Compliance & Hardening | 0 | 0 | 0 | 140 | 170 | 55 | 170 | 55 | 590 | 5
PHASE 7 — Analytics & Reporting
7.1 Dashboard Analytics | 0 | 0 | 0 | 90 | 110 | 30 | 100 | 30 | 360 | 2
7.2 Revenue Reporting | 0 | 0 | 0 | 80 | 100 | 25 | 90 | 30 | 325 | 1.5
7.3 Customer Analytics | 0 | 0 | 0 | 80 | 100 | 25 | 90 | 30 | 325 | 1.5
PHASE 8 — Vertical Polish
8.1 Services Vertical Optimisation | 0 | 0 | 0 | 60 | 80 | 20 | 70 | 25 | 255 | 1.5
8.2 Time Tracking & Billing Polish | 0 | 0 | 0 | 60 | 70 | 20 | 60 | 20 | 230 | 1
8.3 Client Portal Polish | 0 | 0 | 0 | 60 | 70 | 20 | 60 | 20 | 230 | 1
PHASE 9 — Platform Management
9.1 Client Provisioning | 0 | 0 | 0 | 80 | 100 | 30 | 90 | 30 | 330 | 2
9.2 Client Monitoring | 0 | 0 | 0 | 60 | 80 | 20 | 70 | 25 | 255 | 1.5
9.3 Update Distribution | 0 | 0 | 0 | 50 | 70 | 20 | 60 | 20 | 220 | 1
9.4 Billing Automation | 0 | 0 | 0 | 70 | 90 | 25 | 80 | 25 | 290 | 1.5
PHASE 10 — Launch Preparation
10.1 Comprehensive Testing | 0 | 0 | 0 | 0 | 0 | 80 | 160 | 40 | 280 | 3
10.2 Documentation | 0 | 0 | 0 | 50 | 60 | 0 | 0 | 0 | 110 | 1.5
10.3 Production Launch | 0 | 0 | 0 | 40 | 60 | 20 | 40 | 20 | 180 | 1
0
TOTAL PROJECT ESTIMATE | 170 | 45.73 | 98.77 | 2420.05 | 3099.21 | 948.05 | 3031.32 | 999.16 | 10812.29 | 67
🟦 Blue values = Actuals recorded ¦ White/grey = Estimates ¦ Green = Completed stages
Note: C&S app is significantly simpler than the 4-vertical platform. Estimates reflect reduced scope — no e-commerce, no shipping, no hospitality, no memberships.
Actual spend to date (Stages 1.1–1.3): R107.78